## Dashboard
ISTRAC-FMS · V1 Backend Master Tracker
Primary execution source: Backend V1 Complete DOCX; Architecture v2.1 supplies supplemental requirements where V1 is silent. No deadline is assumed.
KPI | Value | Current Phase 1 tracker | Value | Tracker notes | Value
Backend V1 tasks (actual rows) | 80 | Existing tasks | 45 | Architecture additions | 20
Backend V1 story points (actual rows) | 185 | Existing tasks done | 35 | Scope/decision items | 7
Backend tasks Done | 1 | Existing SP | 136 | Source V1 header says | 72 tasks / 168 SP
Backend SP Done | 1 | Existing SP completed | 107 | Section tables sum to | 80 tasks / 197 SP
Backend completion % | 0.5405% | Existing task completion % | 77.78% | Operational baseline | 80 tasks / 185 task-row SP
|  | Existing SP completion % | 78.68%
Backend status | Tasks | Backend section | SP | Control check | Value
Done | 1 | 0 · Infrastructure & Project Setup | 18 | V1 header task count | 72
Partially Done | 2 | 1 · Authentication & Sessions | 19 | V1 header story points | 168
In Progress | 0 | 2 · User Management | 13 | Task-row task count | 80
Needs Rework | 2 | 3 · Department Management | 12 | Task-row story points | 185
Todo | 75 | 4 · File Management | 33 | Task count difference vs header | 8
Scope Review | 0 | 5 · Browse & Search | 9 | SP difference vs header | 17
|  | 6 · Notifications | 10
|  | 7 · CMS | 5
How to use: update Status, Notes, Owner/Week as work progresses. The latest uploaded Phase 1 tracker (by Ayan) is preserved in Existing Phase1 and is the baseline used for current evidence mapping. |  |  | Current Phase 1: 45 tasks / 136 SP / 35 done / 107 SP completed. | Backend V1 remains the main execution tracker; Architecture Additions captures requirements not fully represented in the V1 task list.
|  | 9 · Health & Monitoring | 4
|  | 10 · WebSocket Server | 10
|  | 11 · Middleware (Cross-cutting) | 15
|  | 12 · Core Services (Business Logic) | 26
Status legend: Done = verified by current tracker evidence; Partially Done = evidence exists but V1 acceptance is not fully demonstrated; Needs Rework = current work conflicts with V1; Scope Review = architecture requirement may conflict with or extend V1 scope; Todo = not evidenced yet.

## Backend V1
ID | Section | Method / Task | Description | Acceptance Criteria | Role | Priority | SP | Owner | Spec Week | Tracker Status | Current Evidence / Notes | Column1
IN-001 | 0 · Infrastructure & Project Setup | INFRA Project scaffold | Create src/api/, src/services/, src/repositories/, src/middleware/ Clean Architecture folders. TypeScript strict mode. ESLint + Prettier pre-commit hooks. | tsc --noEmit passes with zero errors. eslint . passes with zero warnings. | BOTH | P1 | 2 | FS | Wk 1 | Todo
IN-002 | 0 · Infrastructure & Project Setup | INFRA MySQL schema — all 9 tables | Create migration files for: users, departments, user_dept_access, hdd_nodes, file_versions, audit_logs, cms_blocks, notifications, system_config. | All FKs, indexes, and ENUMs correct. migration up and down both succeed without errors. | BOTH | P1 | 4 | FS | Wk 1 | Needs Rework | DB-001/DB-002 are Done in the latest tracker, but they are PostgreSQL-oriented; V1 requires MySQL 8.0 and the exact 9-table migration set.
IN-003 | 0 · Infrastructure & Project Setup | INFRA MySQL connection pool + query builder | Configure mysql2 connection pool. Create typed query wrapper. Set up db-migrate for schema versioning. | Pool connects to MySQL on startup. Health check reports db: ok. migrate up runs all pending migrations. | BOTH | P1 | 2 | FS | Wk 1 | Needs Rework | DB-002 is Done in the latest tracker, but V1 requires mysql2 pool + typed query wrapper + db-migrate; current tracker specifies Prisma/Knex.
IN-004 | 0 · Infrastructure & Project Setup | INFRA Redis connection (blacklist + pub-sub) | Redis client for token blacklist (SET with TTL) and pub-sub channels (cms.update, notification.broadcast, hdd.sync). | Health check reports redis: ok. SET/GET/DEL work. Publish on channel received by subscriber in same process. | BOTH | P1 | 2 | FS | Wk 1 | Partially Done | DB-005 is Done: Redis setup + pub/sub. V1 acceptance also requires token-blacklist SET/GET/DEL behavior and the specified channels, which are not explicitly demonstrated in the tracker.
IN-005 | 0 · Infrastructure & Project Setup | INFRA Environment config (.env + validation) | .env.example documents every key: DB_URL, REDIS_URL, JWT_SECRET, REFRESH_SECRET, SMTP_*, HDD_MOUNT_ROOT, UPLOAD_MAX_BYTES. | App fails fast with a clear error if any required key is missing. No secrets hardcoded anywhere in source. | BOTH | P1 | 1 | FS | Wk 1 | Done | DB-004 is Done: environment/secrets configuration and fail-fast .env schema work.
IN-006 | 0 · Infrastructure & Project Setup | INFRA Structured logging (pino) + global error handler | JSON-structured logs with fields: timestamp, level, requestId, userId, method, path, statusCode, durationMs, error. Global Express error handler catches all unhandled errors. | Logs are valid JSON. Unhandled errors return { error: { code, message } } and never expose stack traces in production. | BOTH | P1 | 2 | FS | Wk 1 | Todo | DB-008 is still Todo in the latest tracker; no completed evidence for the V1 pino structured fields + global error handler acceptance criteria.
IN-007 | 0 · Infrastructure & Project Setup | INFRA OpenAPI 3.0 spec + Swagger UI at /api/docs | swagger-jsdoc or manual spec covering all 45 endpoints. Swagger UI served at /api/docs (intranet only). | /api/docs loads without 404. All endpoints present with request/response schemas. | BOTH | P2 | 3 | FS | Wk 2 | Partially Done | DB-007 is Done: API mock/contract layer. V1 acceptance requires Swagger UI at /api/docs covering all 45 endpoints with request/response schemas; not fully demonstrated.
IN-008 | 0 · Infrastructure & Project Setup | INFRA HDD mount root validation on startup | On app start, verify MOUNT_ROOT (/mnt/istrac-data) exists and is writable. If not, log FATAL and exit. | App exits with code 1 and clear message if HDD not mounted. /health endpoint reports hdd: unavailable if mount disappears at runtime. | BOTH | P1 | 2 | FS | Wk 1 | Todo
AU-001 | 1 · Authentication & Sessions | POST /auth/register | New user submits form. Account created with status=PENDING. Admin notified. | 201 + { userId }. Duplicate email or employee_id → 409. Admin receives in-app notification + email via EmailService. | PUBLIC | P1 | 3 | BE | Wk 2 | Todo
AU-002 | 1 · Authentication & Sessions | POST /auth/login | Validate email + bcrypt password (cost 12). Issue JWT access (15 min) in response body + httpOnly refresh cookie (7 day). | Wrong creds → 401 with attempts_remaining. 5 failures → 15-min lockout stored in Redis. temp_pass=true → 200 with force_change flag. | PUBLIC | P1 | 3 | BE | Wk 2 | Todo
AU-003 | 1 · Authentication & Sessions | POST /auth/refresh | Validate refresh token from httpOnly cookie. Issue new access token. Rotate refresh token (old immediately blacklisted in Redis). | Expired/blacklisted token → 401. New access + refresh tokens issued. Old refresh token added to Redis blacklist with TTL. | BOTH | P1 | 2 | BE | Wk 2 | Todo
AU-004 | 1 · Authentication & Sessions | POST /auth/logout | Add current refresh token to Redis blacklist. Clear httpOnly cookie. | Token blacklisted. Cookie cleared (Max-Age=0). Subsequent refresh with same token → 401. | BOTH | P1 | 1 | BE | Wk 2 | Todo
AU-005 | 1 · Authentication & Sessions | POST /auth/change-password | Authenticated user changes own password. Validates old password + policy (10 chars, upper/lower/digit/special). Invalidates ALL sessions. | bcrypt verify old password. Policy enforced. Last 5 hashes checked (no reuse). All refresh tokens for this user blacklisted. Audit logged. | BOTH | P1 | 3 | BE | Wk 2 | Todo
AU-006 | 1 · Authentication & Sessions | POST /auth/forgot-password | Accept email. If account exists, send 6-digit OTP via SMTP. Always return 200 (no enumeration). | OTP stored as bcrypt hash in Redis with 15-min TTL. Max 3 OTP requests/hour per email (Redis counter). Email sent via EmailService. | PUBLIC | P1 | 2 | BE | Wk 2 | Todo
AU-007 | 1 · Authentication & Sessions | POST /auth/reset-password | Validate OTP from Redis + set new password. Invalidate all sessions. | Wrong/expired OTP → 400. Valid OTP is single-use (deleted from Redis on use). All sessions blacklisted. Audit logged. | PUBLIC | P1 | 2 | BE | Wk 2 | Todo
AU-008 | 1 · Authentication & Sessions | GET /auth/me | Return current user profile (id, name, email, role, status, depts). | 401 if token missing/invalid. Response includes list of assigned department IDs. Password never returned. | BOTH | P1 | 1 | BE | Wk 2 | Todo
AU-009 | 1 · Authentication & Sessions | PATCH /auth/me | Update own name or notification_opt_in preference. | Cannot change role, status, email, or employee_id via this endpoint. Returns updated profile. Audit logged. | BOTH | P2 | 2 | BE | Wk 3 | Todo
UM-001 | 2 · User Management | GET /admin/users | Paginated list of all users with role, status, assigned departments. | Supports ?status=PENDING¦ACTIVE¦SUSPENDED&search=name_or_email&page=&limit=20. Cursor-based pagination envelope. 403 if non-admin. | ADMIN | P1 | 2 | BE | Wk 3 | Todo
UM-002 | 2 · User Management | GET /admin/users/pending | List all PENDING users awaiting approval. Used by Approval Queue. | Returns pending users ordered by createdAt ascending (oldest first). Includes name, email, employee_id, dept_preference, reason_for_access. | ADMIN | P1 | 1 | BE | Wk 3 | Todo
UM-003 | 2 · User Management | POST /admin/users/:id/approve | Approve a PENDING user. Generate 8-char temp password. Send approval email. | User status → ACTIVE. temp_pass = true. Email sent with temp password via EmailService. In-app notification sent to user. Audit logged. | ADMIN | P1 | 3 | BE | Wk 3 | Todo
UM-004 | 2 · User Management | POST /admin/users/:id/reject | Reject a PENDING user. Body: { reason }. | User status → REJECTED. Reason emailed to user. In-app notification sent. Audit logged. reason field required. | ADMIN | P1 | 2 | BE | Wk 3 | Todo
UM-005 | 2 · User Management | POST /admin/users/:id/suspend | Suspend an ACTIVE user. Immediately invalidate all their sessions. | User status → SUSPENDED. All refresh tokens blacklisted in Redis. In-app notification sent to user. Audit logged. | ADMIN | P1 | 2 | BE | Wk 3 | Todo
UM-006 | 2 · User Management | POST /admin/users/:id/force-logout | Instantly invalidate all sessions for a user without changing their status. | All refresh tokens for userId blacklisted. User gets 401 on next request with message: session_terminated_by_admin. | ADMIN | P1 | 2 | BE | Wk 3 | Todo
UM-007 | 2 · User Management | GET /admin/users/:id | Get complete profile of any user. | Returns full user record including status, depts, lastLogin, createdAt. Password hash never included. 403 if non-admin. | ADMIN | P2 | 1 | BE | Wk 3 | Todo
DM-001 | 3 · Department Management | GET /departments | List all active departments with file count and last-updated date. | Returns { id, name, fileCount, lastUpdated } for each dept. Both roles can see the list. Archived depts excluded. | BOTH | P1 | 1 | BE | Wk 3 | Todo
DM-002 | 3 · Department Management | POST /departments | Admin creates a new department with name and HDD path. | Name must be unique. hdd_path validated to be inside MOUNT_ROOT. Directory created on HDD if it does not exist. Audit logged. | ADMIN | P1 | 2 | BE | Wk 3 | Todo
DM-003 | 3 · Department Management | PUT /departments/:id | Admin updates department name or description. | Name uniqueness re-validated. Audit logged. 404 if dept not found. | ADMIN | P2 | 2 | BE | Wk 3 | Todo
DM-004 | 3 · Department Management | DELETE /departments/:id | Admin soft-archives a department. | Sets archived_at = NOW(). Files remain on HDD and in DB. Dept no longer appears in GET /departments. Audit logged. | ADMIN | P2 | 2 | BE | Wk 4 | Todo
DM-005 | 3 · Department Management | POST /departments/:id/users | Admin assigns a user to a department. Body: { userId, accessLevel }. | accessLevel must be READ_ONLY or READ_WRITE (V1 — no DELETE level for users). Upserts user_dept_access record. In-app notification sent to user. Audit logged. | ADMIN | P1 | 3 | BE | Wk 3 | Todo
DM-006 | 3 · Department Management | DELETE /departments/:id/users/:userId | Admin removes a user from a department. | Deletes user_dept_access record. User can no longer see or download files from that dept. Audit logged. | ADMIN | P1 | 2 | BE | Wk 3 | Todo
FM-001 | 4 · File Management | POST /files/upload | Admin uploads a file to a specific department. Single-shot for files <= 10 MB. | Magic-byte validation (real type, not just extension). SHA-256 checksum computed and stored. Atomic HDD write: write to temp path then rename. DB insert + audit log in single MySQL transaction (rollback if either fails). WS broadcast FILE_UPLOAD to all users assigned to this dept. | ADMIN | P1 | 5 | BE | Wk 4 | Todo
FM-002 | 4 · File Management | POST /files/upload/chunk | Upload a single chunk for large files (> 10 MB). Body: multipart with chunkIndex, totalChunks, sessionId. | First request creates upload_session record in DB. Each chunk saved to /tmp/uploads/{sessionId}/chunk_{n}. Returns { sessionId, received: chunkIndex }. | ADMIN | P2 | 3 | BE | Wk 4 | Todo
FM-003 | 4 · File Management | POST /files/upload/complete | Finalise chunked upload. Assemble, verify checksum, commit to HDD + DB. | Assembles chunks in order. Verifies client-provided SHA-256. On mismatch → 422 + cleanup. On success → same DB + audit + WS flow as FM-001. Temp chunks deleted from /tmp. | ADMIN | P2 | 3 | BE | Wk 4 | Todo
FM-004 | 4 · File Management | GET /files | List files. Admin sees ALL files. User sees only files in their assigned departments. | Supports ?deptId=&type=&search=&sort=name¦date¦size&order=asc¦desc&page=. Admin: includes soft-deleted files (deleted_at not null). User: excludes deleted files. Paginated (20/page, cursor-based). | BOTH | P1 | 3 | BE | Wk 4 | Todo
FM-005 | 4 · File Management | GET /files/:id | Get metadata for a single file. | Returns name, size, mimeType, sha256, uploader, deptId, createdAt, versionCount, deletedAt (admin only). HDD path never exposed. User: 404 if file is in a dept they are not assigned to. | BOTH | P1 | 1 | BE | Wk 4 | Todo
FM-006 | 4 · File Management | GET /files/:id/download | Stream file bytes from HDD to client. | Streamed via fs.createReadStream — never fully loaded to memory. Range header supported (resumable downloads). SHA-256 recomputed on stream; 409 on mismatch. Audit log: FILE_DOWNLOAD. User: 403 if not assigned to file dept. | BOTH | P1 | 4 | BE | Wk 4 | Todo
FM-007 | 4 · File Management | PATCH /files/:id | Admin updates file metadata: description, tags. | Only description and tags editable. Name/path not changeable. FULLTEXT index updated. Audit logged. | ADMIN | P2 | 2 | BE | Wk 5 | Todo
FM-008 | 4 · File Management | DELETE /files/:id | Soft-delete a file. Moves bytes to /_trash/{deptId}/ on HDD. | Sets deleted_at = NOW() on hdd_nodes. Bytes moved (not copied) to MOUNT_ROOT/_trash/{deptId}/. File invisible to users. Audit logged with admin identity. | ADMIN | P1 | 3 | BE | Wk 5 | Todo
FM-009 | 4 · File Management | POST /files/:id/restore | Restore a soft-deleted file. Moves bytes back from trash. | Clears deleted_at. Bytes moved back to original dept path. Visible again to users. Audit logged. | ADMIN | P2 | 2 | BE | Wk 5 | Todo
FM-010 | 4 · File Management | GET /files/:id/versions | List all versions of a file. Ordered newest-first. | Returns array: { versionNum, createdAt, uploadedBy, sizeBytes, sha256 }. User: 403 if not assigned to file dept. | BOTH | P2 | 2 | BE | Wk 5 | Todo
FM-011 | 4 · File Management | GET /files/:id/versions/:vnum/download | Download a specific previous version. | Resolves path from MOUNT_ROOT/_versions/{fileId}/{vnum}/. Same stream + checksum logic as FM-006. Audit logged. | BOTH | P2 | 2 | BE | Wk 5 | Todo
FM-012 | 4 · File Management | POST /files/:id/versions | Upload a new version of an existing file (same name, same dept). Admin only. | Previous file moved to MOUNT_ROOT/_versions/{fileId}/{n}/. version_count incremented. New hdd_nodes record linked in file_versions. SELECT FOR UPDATE prevents concurrent version conflicts (409 on race). | ADMIN | P2 | 3 | BE | Wk 5 | Todo
BS-001 | 5 · Browse & Search | GET /browse/:deptId | Navigate folder tree for a department. Returns hdd_nodes with node_type=FOLDER as a tree. | Supports ?parentId= (root if omitted). Returns { id, name, parentId, childCount }. User: 403 if not assigned to deptId. Admin: sees all folders including those with only deleted files. | BOTH | P1 | 3 | BE | Wk 5 | Todo
BS-002 | 5 · Browse & Search | GET /browse/:deptId/folder/:folderId/files | List files inside a specific folder. Paginated. | Returns files in the folder (node_type=FILE, parentId=folderId). User: excludes deleted files and unassigned depts. Supports ?sort=name¦date¦size&order=asc¦desc&page=. | BOTH | P1 | 2 | BE | Wk 5 | Todo
BS-003 | 5 · Browse & Search | GET /search | Full-text search across files. MySQL FULLTEXT on name, description, tags. | Supports ?q=&deptId=&type=&before=&after=&page=. User: results scoped to assigned departments only (cross-dept leak impossible). Returns paginated file metadata with relevance ordering. | BOTH | P1 | 4 | BE | Wk 5 | Todo
NT-001 | 6 · Notifications | POST /notifications/broadcast | Admin sends a message to ALL users or users of a specific department. Body: { title, message, targetDeptId? }. | Notification record inserted for each recipient. Redis PUBLISH on notification.broadcast channel → WebSocket delivers instantly. Audit logged. | ADMIN | P1 | 3 | BE | Wk 5 | Todo
NT-002 | 6 · Notifications | GET /notifications | Current user paginated notification inbox. | Supports ?category=Files¦System¦Approvals&unread=true&cursor=&limit=30. Cursor-based pagination (append-only table). Returns only the requesting user own notifications. Ordered newest-first. | BOTH | P1 | 2 | BE | Wk 5 | Todo
NT-003 | 6 · Notifications | GET /notifications/count | Lightweight unread count for bell badge. | SELECT COUNT(*) WHERE userId = ? AND read_at IS NULL. Response: { unread: number }. No pagination needed. | BOTH | P1 | 1 | BE | Wk 5 | Todo
NT-004 | 6 · Notifications | PATCH /notifications/:id/read | Mark a single notification as read. | Sets read_at = NOW(). User can only mark their own notifications (403 otherwise). Returns updated notification. | BOTH | P2 | 1 | BE | Wk 6 | Todo
NT-005 | 6 · Notifications | POST /notifications/mark-all-read | Mark all unread notifications as read for the current user. | UPDATE notifications SET read_at = NOW() WHERE userId = ? AND read_at IS NULL. Returns { marked: count }. | BOTH | P2 | 1 | BE | Wk 6 | Todo
NT-006 | 6 · Notifications | DELETE /notifications/:id | Dismiss (hide) a single notification. | Sets dismissed_at = NOW(). User can only dismiss their own. Dismissed notifications excluded from GET /notifications. | BOTH | P3 | 1 | BE | Wk 6 | Todo
NT-007 | 6 · Notifications | POST /notifications/dismiss-read | Dismiss all already-read notifications for current user. | Sets dismissed_at = NOW() WHERE userId = ? AND read_at IS NOT NULL. Returns { dismissed: count }. | BOTH | P3 | 1 | BE | Wk 6 | Todo
CM-001 | 7 · CMS | GET /cms | Return all CMS content blocks as a key-value map. No auth required. | Returns { hero_title, hero_subtitle, hero_cta_text, announcement_text, announcement_visible, gallery_items, banner_title, banner_visible, org_overview, contact_info, sections_visibility }. | PUBLIC | P1 | 1 | BE | Wk 6 | Todo
CM-002 | 7 · CMS | PUT /cms/:blockKey | Admin updates a single CMS block by key. | blockKey must be in allowlist (prevent arbitrary injection). Value saved to cms_blocks table. Redis PUBLISH on cms.update channel → WebSocket delivers to all connected clients. Landing page updates without reload. Audit logged. | ADMIN | P1 | 3 | BE | Wk 6 | Todo
CM-003 | 7 · CMS | GET /admin/cms/preview | Return all CMS blocks including toggled-off sections. Admin preview only. | 403 if non-admin. Used by CMS live-preview iframe in Phase 1 frontend. | ADMIN | P2 | 1 | BE | Wk 6 | Todo
AD-001 | 8 · Admin Dashboard & System Config | GET /admin/stats | System statistics for admin home dashboard. | Returns { totalUsers, activeUsers, pendingUsers, suspendedUsers, totalFiles, deletedFiles, totalDepts, storageUsedBytes, recentAuditEntries: last 10 }. storageUsedBytes = SUM(size_bytes) from hdd_nodes WHERE deleted_at IS NULL. | ADMIN | P1 | 2 | BE | Wk 6 | Todo
AD-002 | 8 · Admin Dashboard & System Config | GET /admin/audit-logs | Paginated, filterable audit log. | Supports ?userId=&action=&from=&to=&cursor=&limit=20. Cursor-based on BIGINT id (append-only). Returns entries with actor name, resource type/id, old/new values. | ADMIN | P1 | 2 | BE | Wk 6 | Todo
AD-003 | 8 · Admin Dashboard & System Config | GET /admin/audit-logs/export | Export filtered audit log as CSV download. | Same filters as AD-002. Streams CSV with headers. Content-Disposition: attachment; filename=audit_log_{date}.csv. | ADMIN | P2 | 2 | BE | Wk 7 | Todo
AD-004 | 8 · Admin Dashboard & System Config | GET /admin/settings | Return all runtime configuration values from system_config table. | Returns all key-value pairs. Keys: max_upload_bytes, allowed_extensions, hdd_sync_interval_minutes, download_rate_limit_per_hour, smtp_enabled. | ADMIN | P2 | 1 | BE | Wk 7 | Todo
AD-005 | 8 · Admin Dashboard & System Config | PUT /admin/settings/:key | Update a runtime config value. No server restart needed. | Key must be in allowlist. Written to system_config table. In-memory config cache invalidated (TTL 60s). Audit logged. | ADMIN | P2 | 2 | BE | Wk 7 | Todo
AD-006 | 8 · Admin Dashboard & System Config | POST /admin/hdd-sync | Manually trigger HDD sync daemon. | Runs HddSyncService.run() asynchronously. Returns { jobId, status: started } immediately. On completion: Redis PUBLISH on hdd.sync → WS event SYNC_COMPLETE sent to admin. | ADMIN | P2 | 2 | BE | Wk 7 | Todo
HL-001 | 9 · Health & Monitoring | GET /health | Application health check. Returns DB + Redis + HDD mount status. | Returns 200: { status: ok, db: ok¦error, redis: ok¦error, hdd: ok¦error, timestamp }. Returns 503 if any dependency is down. No auth required. | PUBLIC | P1 | 2 | FS | Wk 2 | Todo
HL-002 | 9 · Health & Monitoring | GET /admin/health/hdd | Detailed HDD health: last check time, mount path, available bytes, last failure. | Admin only. Checks if MOUNT_ROOT is accessible by reading a probe file. Returns { mounted, lastChecked, availableBytes, lastFailure }. | ADMIN | P2 | 2 | FS | Wk 7 | Todo
WS-001 | 10 · WebSocket Server | WS /ws (connect) | JWT validated on handshake. User associated with socket. Ping/pong keepalive every 30s. | Client sends ?token=<accessToken> on connect. Invalid/expired token → close code 4401. 3 missed pings → socket closed and cleaned from connection map. Connection count exposed in /health. | BOTH | P1 | 4 | FS | Wk 2 | Todo
WS-002 | 10 · WebSocket Server | WS /ws (outbound events) | Server → client events: FILE_UPLOAD, FILE_DELETED, NOTIFICATION, CMS_UPDATE, SYNC_COMPLETE, APPROVAL_RESULT. | FILE_UPLOAD → users assigned to that deptId only. FILE_DELETED → users assigned to that deptId only. NOTIFICATION → targeted userId or broadcast to all. CMS_UPDATE → all connected users. SYNC_COMPLETE → admin only. APPROVAL_RESULT → specific user. | BOTH | P1 | 4 | FS | Wk 2 | Todo
WS-003 | 10 · WebSocket Server | WS /ws (Redis pub-sub bridge) | Subscribe to Redis channels and fan-out to connected WebSocket clients. | Channels: notification.broadcast, cms.update, hdd.sync. Message received on Redis channel → forwarded to appropriate WS sockets. Handles multiple Node.js processes if scaled via PM2 cluster. | BOTH | P1 | 2 | FS | Wk 2 | Todo
MW-001 | 11 · Middleware (Cross-cutting) | MW authMiddleware | Verify JWT access token on every protected route. Check Redis blacklist for revoked tokens. Attach req.user. | Missing token → 401. Expired token → 401 with code token_expired. Blacklisted token → 401 with code token_revoked. req.user = { id, role, deptIds } on success. | BOTH | P1 | 3 | FS | Wk 2 | Todo
MW-002 | 11 · Middleware (Cross-cutting) | MW isAdminMiddleware | Verify req.user.role === ADMIN. Applied to all /admin/* routes and admin-only file operations. | 403 { code: forbidden } if role is USER. Never applied to PUBLIC or BOTH routes. | BOTH | P1 | 2 | FS | Wk 2 | Todo
MW-003 | 11 · Middleware (Cross-cutting) | MW deptAccessMiddleware | For file/browse routes: verify user has access to the target department. Admin bypasses check. | Reads deptId from params or body. Checks user_dept_access table (cached in Redis for 5 min). 403 if user not assigned to dept. | BOTH | P1 | 3 | FS | Wk 3 | Todo
MW-004 | 11 · Middleware (Cross-cutting) | MW rateLimiterMiddleware | Two rate limiters: login (5 failures per IP → 15 min lockout) and download (100 per user per hour). | Login lockout stored in Redis with TTL. Download count stored in Redis sliding window. Exceeded limits return 429 with Retry-After header. Anomaly alert if user downloads > 50 files in 10 min. | BOTH | P1 | 3 | FS | Wk 3 | Todo
MW-005 | 11 · Middleware (Cross-cutting) | MW auditMiddleware | Automatically log every state-changing request (POST/PUT/PATCH/DELETE) to audit_logs after response is sent. | Captures: userId, action (derived from method+path), resourceType, resourceId, ip_address, user_agent, statusCode. Runs async after response — never blocks the request. | BOTH | P1 | 2 | FS | Wk 2 | Todo
MW-006 | 11 · Middleware (Cross-cutting) | MW hddAvailabilityMiddleware | Applied to upload/download routes. Verify HDD mount is accessible before processing. | If MOUNT_ROOT probe fails → 503 { code: hdd_unavailable }. Sends admin notification on first failure. Caches check result for 30s to avoid hammering disk. | BOTH | P1 | 2 | FS | Wk 3 | Todo
SV-001 | 12 · Core Services (Business Logic) | SVC HddService | Low-level HDD I/O: write, read/stream, move, delete, generate checksum, validate magic bytes. | writeFile: temp path → atomic rename. streamFile: returns ReadableStream. moveFile: handles cross-path move within MOUNT_ROOT. validateMagicBytes: checks first 8 bytes against known signatures. All paths validated against MOUNT_ROOT boundary (path traversal guard). | BOTH | P1 | 4 | FS | Wk 3 | Todo
SV-002 | 12 · Core Services (Business Logic) | SVC HddSyncService | Daemon that walks the HDD tree every N minutes (configurable). Reconciles HDD state with DB. | Files on HDD not in DB → inserted as status=UNREGISTERED. Files in DB but missing from HDD → marked status=ORPHANED. Files in both → updated last_synced, size_bytes. On completion: emit SYNC_COMPLETE event via Redis pub-sub. | BOTH | P1 | 4 | FS | Wk 4 | Todo
SV-003 | 12 · Core Services (Business Logic) | SVC AuditService | Append-only audit logger. All mutations logged with actor, resource, old/new JSON. | INSERT only — no UPDATE or DELETE ever on audit_logs. Async (non-blocking). DB user for audit inserts has INSERT-only privilege on this table. | BOTH | P1 | 2 | FS | Wk 2 | Todo
SV-004 | 12 · Core Services (Business Logic) | SVC EmailService | Nodemailer + campus SMTP. Templates for: approval, rejection, suspension, OTP, broadcast. | All email stays on intranet SMTP. Errors logged but never propagate to API response. Templates use plain text + HTML. SMTP credentials from .env. | BOTH | P1 | 3 | BE | Wk 2 | Todo
SV-005 | 12 · Core Services (Business Logic) | SVC NotificationService | Single entry point for creating notification records + pushing via WebSocket. | send({ type, actorId, recipientIds, message, metadata }): INSERT to notifications for each recipient, then Redis PUBLISH for real-time delivery. Non-blocking — errors never cause transaction rollback. | BOTH | P1 | 3 | FS | Wk 3 | Todo
SV-006 | 12 · Core Services (Business Logic) | SVC FileService | Orchestrates upload: validate → HDD write → DB insert (transaction) → audit → notification. | Compensation pattern: if DB insert fails after HDD write → immediately delete HDD file. SELECT FOR UPDATE before write to prevent concurrent version conflict. SHA-256 computed and stored. All DB ops in a single MySQL transaction. | BOTH | P1 | 5 | FS | Wk 4 | Todo
SV-007 | 12 · Core Services (Business Logic) | SVC SearchService | MySQL FULLTEXT search on hdd_nodes(name, description, tags). Results scoped to user dept access. | MATCH AGAINST in BOOLEAN MODE. JOIN with user_dept_access to scope results. Admin sees all including deleted. User sees non-deleted only. | BOTH | P1 | 3 | BE | Wk 5 | Todo
SV-008 | 12 · Core Services (Business Logic) | SVC HddHealthService | Background probe every 60s. Admin email + system banner on failure. | Writes and reads a .probe file at MOUNT_ROOT. On failure: send admin email once (not every 60s). Set system-wide hdd_degraded flag in Redis. On recovery: send recovery email. Clear flag. | BOTH | P1 | 2 | FS | Wk 3 | Todo

## Architecture Additions
ID | Area | Supplemental Task | Requirement / Work | Acceptance Criteria | Priority | Source | Status | Why It Was Added
ARCH-V1-001 | Security | Nginx security headers | Configure HSTS, X-Frame-Options, X-Content-Type-Options, Referrer-Policy and CSP on all responses; hide server fingerprinting headers. | Headers verified in staging with an automated smoke/security check; HTTPS redirect works. | P1 | Architecture Ch. 7.2.1 / 11.3 | Todo | Missing from V1 task list
ARCH-V1-002 | Security | CSRF protection for refresh/logout | SameSite=Strict refresh cookie plus X-CSRF-Token validation on cookie-dependent state-changing auth endpoints; rotate CSRF token on refresh. | Cross-site request without valid CSRF header is rejected; token rotates after refresh. | P1 | Architecture Ch. 7.2.2 | Todo | Missing from V1 task list
ARCH-V1-003 | Security | Restrictive CORS policy | Set CORS origin from APP_ORIGIN; never wildcard. Explicitly allow GET/POST/PUT/DELETE/PATCH and Authorization, Content-Type, X-CSRF-Token headers. | Preflight and API tests pass for allowed origin and fail for disallowed origin. | P1 | Architecture Ch. 7.2.3 | Todo | Missing from V1 task list
ARCH-V1-004 | Authentication | TOTP MFA for Super Admin | Implement RFC 6238 TOTP MFA for the bootstrapped/admin account and add mfa_secret handling without exposing the secret. | Admin cannot complete authentication without valid MFA once enabled; backup/recovery behavior documented. | P1 | Architecture Ch. 5.7; REQ-AUTH-05 | Scope Review | Architecture requirement; validate against V1 2-role scope
ARCH-V1-005 | API | Standard error envelope + requestId | All errors use {error:{code,message,details},requestId}; stable codes documented in OpenAPI. | All protected/public error paths return the standard envelope; requestId is traceable in logs. | P1 | Architecture Ch. 9.4; REQ-API-02 | Todo | V1 global error handler only partially covers this
ARCH-V1-006 | WebSocket | Reconnect contract with exponential backoff | Document/implement client contract: 1s,2s,4s,8s,16s then 60s; after reconnect re-fetch notification inbox. | Reconnect sequence and missed-message recovery verified in E2E. | P1 | Architecture Ch. 12.4; REQ-WS-03 | Todo | Backend + frontend coordination required
ARCH-V1-007 | Testing | Unit test coverage ≥80% | Jest service/middleware tests with dependency injection and mocked I/O; minimum 80% line coverage for services + middleware. | Coverage report ≥80%; unit suite under 30 seconds. | P1 | Architecture Ch. 14.3; REQ-TEST-01 | Todo | Missing from V1 task list
ARCH-V1-008 | Testing | REST integration tests for every endpoint | Jest + Supertest against a real MySQL test DB/schema; cover each V1 REST endpoint. | Every V1 REST endpoint has at least one integration test; failures block CI. | P1 | Architecture Ch. 14.4; REQ-TEST-02 | Todo | Missing from V1 task list
ARCH-V1-009 | Testing | Critical E2E backend journeys | Automate critical flows: register→approve→login→upload→user access→download; suspend→session invalidation; CMS→WS update. | Critical journey tests pass in a reproducible test environment. | P1 | Architecture Ch. 14.5; REQ-TEST-03 | Todo | Missing from V1 task list
ARCH-V1-010 | Testing | CI pipeline gates | CI runs lint, unit/integration tests and build; failing checks block merge; deploy to staging after approval/merge workflow. | Protected branch cannot merge when required checks fail. | P1 | Architecture Ch. 14.7; REQ-TEST-04 | Todo | Existing DB-006 is only frontend/project-level CI and is Todo
ARCH-V1-011 | Observability | PM2 log rotation + uptime monitoring | Rotate logs at 100 MB with 30-day retention; catch unhandled exceptions/rejections; configure internal /api/v1/health uptime check with alerting. | Logs rotate automatically; uptime monitor alerts after 3 consecutive failures. | P1 | Architecture Ch. 7.5; REQ-OBS-01/02 | Todo | Logging/health are only partial in existing tracker
ARCH-V1-012 | Disaster Recovery | Backup verification + DR runbook | Daily MySQL dump (30-day retention), HDD/NAS RAID1 or nightly rsync backup, secure .env backup; document restore sequence and smoke tests. | A documented restore drill succeeds in staging; backup files are verified and recoverable. | P1 | Architecture Ch. 11.5–11.6 | Todo | Missing from V1 task list
ARCH-V1-013 | Disaster Recovery | RPO/RTO and quarterly DR drill | Adopt RPO ≤24h and RTO ≤4h; perform quarterly staging restore drill and record results. | Latest drill evidence stored in repo/ops record and meets targets. | P1 | Architecture Ch. 11.6 | Todo | Missing from V1 task list
ARCH-V1-014 | Environments | Dev/staging/production parity | Maintain named dev, staging and production environments; staging mirrors production versions/config shape; migrations validated in staging first. | Separate env config files exist; a staging migration validation step is documented/automated. | P1 | Architecture Ch. 2.4 | Partially Done | Docker Compose in current tracker covers local dev only; staging parity is not shown
ARCH-V1-015 | Folder Management | User subfolder creation permissions | READ_WRITE users may create subfolders when allow_user_folder_creation is enabled; folder depth configurable (default max 5). | RBAC tests enforce create/browse restrictions and max depth. | P1 | Architecture Ch. 4.5; REQ-RBAC-03 | Scope Review | Missing from V1 endpoint list; confirm whether this is V1 or V2
ARCH-V1-016 | File Management | Bulk file operations | Provide backend support for bulk delete/tag/move operations with department-scoped authorization and audit logging. | Bulk action is atomic/compensated as specified, rejects unauthorized cross-dept items, and audits each affected file. | P2 | Architecture Ch. 6.6; REQ-FILE-06 | Scope Review | Architecture gap; current frontend FE-022 expects bulk delete/tag
ARCH-V1-017 | Identity | LDAP/Active Directory integration | Passport.js LDAP authentication; map AD identity to local employee_id; unknown identities become PENDING; no LDAP password storage. | LDAP login and approval mapping work against test directory; local password fallback limited to bootstrapped admin. | P1 | Architecture Ch. 10.6; REQ-AUTH-06 | Scope Review | Critical architecture requirement but absent from V1 complete task list
ARCH-V1-018 | Data Model | Normalize tags | Replace comma-separated tag storage with normalized tags + junction table if architecture decision is adopted. | Tag search/autocomplete works without parsing CSV strings; migration path documented. | P3 | Architecture Ch. 8.3 / 13.2 | Deferred (V1.1) | Architecture labels this as a minor gap; not a V1 launch blocker
ARCH-V1-019 | Security | File encryption at rest (optional) | Optional AES-256-GCM per-department encryption with keys stored separately from protected files. | Encrypted department can upload/download successfully and keys are not stored beside files. | P3 | Architecture Ch. 7.2.4 / 13.3 | Deferred (V1.1) | Architecture explicitly treats this as optional / V1.1
ARCH-V1-020 | File Sharing | Intranet share links with expiry | Generate expiring intranet share links scoped to files and authorized department access. | Expired/invalid links fail; share access is audited. | P3 | Architecture Ch. 6.7; REQ-FILE-07 | Deferred (V1.1) | Architecture gap but not present in current V1 endpoint list

## Existing Phase1
ISTRAC-FMS · Phase 1 Task Tracker
45 Tasks · 136 Story Points · Weeks 1-4 · P1=Critical P2=High P3=Nice-to-have
ID | Category | Task | Acceptance Criteria | Priority | SP | Week | Status | Notes
FE-001 | 1 · Design System & Project Setup | Configure Tailwind CSS — custom color tokens, spacing scale, font scale | tailwind.config.ts exports Navy/Orange/Slate tokens; build produces correct output. | P1 | 2 | Week 1 | Done
FE-002 | 1 · Design System & Project Setup | Base component library: Button, Badge, Input, Modal, Card, Table, Avatar | ≥2 variants each, renders without errors, exported from components/index.ts, demo page. | P1 | 5 | Week 1 | Done
FE-003 | 1 · Design System & Project Setup | Font loading — Lato (thin/light/regular/bold) + DejaVu Sans Mono for code | Fonts load via @font-face or CDN fallback; no FOUT on first paint. | P2 | 1 | Week 1 | Done
FE-004 | 1 · Design System & Project Setup | React Router v6 config — public / protected (JWT) / admin (RBAC) routes | Unauth user → /login. Non-admin → /dashboard. Nested layouts work. | P1 | 2 | Week 1 | Done
FE-005 | 1 · Design System & Project Setup | React Query client + Zustand store (auth / UI / notification slices) | useAuthStore().user populated post-login; devtools show correct keys; persist survives refresh. | P1 | 3 | Week 1 | Done
FE-006 | 1 · Design System & Project Setup | Axios instance — JWT interceptor, silent refresh on 401, redirect on failure | Refresh happens silently; expired refresh token redirects to /login. | P1 | 3 | Week 1 | Done
FE-007 | 2 · Landing Page (CMS-driven) | Hero section — title, subtitle, CTA from AppContext.cmsBlocks | CMS edit updates page without reload (WS push); CTA → /register. | P2 | 3 | Week 1 | Done
FE-008 | 2 · Landing Page (CMS-driven) | Announcement bar — toggleable, text + background from CMS | Admin toggles visibility/text; reflects within 2s via WS. | P2 | 2 | Week 1 | Done
FE-009 | 2 · Landing Page (CMS-driven) | Feature strip — 3-item grid with icon, title, description, individually toggleable | Each item hides independently; 3-col desktop / 1-col mobile. | P2 | 2 | Week 2 | Todo
FE-010 | 2 · Landing Page (CMS-driven) | Gallery section — image cards (URL, label, caption), admin add/remove | New card appears after WS push; empty gallery hides section. | P3 | 3 | Week 2 | Todo
FE-011 | 2 · Landing Page (CMS-driven) | Banner section — title, subtitle, CTA text, visibility toggle | Toggle hides section without reload; CTA hidden if text empty. | P3 | 2 | Week 2 | Todo
FE-012 | 3 · Authentication UI | Login page — email/password, error states, loading spinner, forgot-password link | Field-level errors; spinner on submit; success → /dashboard; lockout counter shown. | P1 | 3 | Week 1 | Done
FE-013 | 3 · Authentication UI | Register page — name, email, employee_id, dept_preference, reason_for_access | Zod client validation; success shows pending-approval message; blocks re-submit. | P1 | 3 | Week 1 | Done
FE-014 | 3 · Authentication UI | Forgot Password — email → OTP → new password | Step 1 masks unknown emails; OTP field blocks paste; wrong OTP errors; success → login. | P1 | 3 | Week 2 | Done
FE-015 | 3 · Authentication UI | Forced password-change screen (shown when temp_pass = true) | Cannot navigate away; strength meter must reach Strong; clears temp_pass on success. | P1 | 2 | Week 2 | Done
FE-016 | 3 · Authentication UI | Password strength meter with live requirement checklist | Each requirement turns green as met; submit disabled until all pass. | P2 | 2 | Week 2 | Done
FE-017 | 4 · Admin Dashboard & AppShell | Sidebar (collapsible, role-gated) + Topbar (bell badge, avatar menu) | Non-admin hides /admin/* links; badge shows unread count; sidebar collapses on mobile. | P1 | 4 | Week 2 | Done
FE-018 | 4 · Admin Dashboard & AppShell | Admin home — stats cards (users/files/depts/storage) + activity feed | Cards pull live data from /admin/stats; feed shows last 10 audit entries. | P1 | 4 | Week 2 | Done
FE-019 | 4 · Admin Dashboard & AppShell | Approval Queue — pending registrations, Approve/Reject + reason modal | Approve removes from queue + toast; rejection reason required and emailed. | P1 | 4 | Week 2 | Done
FE-020 | 4 · Admin Dashboard & AppShell | User Management table — paginated, searchable, filter by status/role | 20/page cursor pagination; Suspend confirms; Force Logout invalidates session instantly. | P1 | 3 | Week 3 | Done
FE-021 | 5 · Admin File Manager & Upload | Department Manager — create/edit/archive depts, HDD mount path, access rules | Name-uniqueness validated; path shows /mnt/istrac-data/ prefix; archive moves to Archived tab. | P1 | 4 | Week 2 | Done
FE-022 | 5 · Admin File Manager & Upload | Per-dept file grid — grid/list toggle, sort, bulk checkbox select | View choice persists in Zustand; bulk bar offers delete + tag. | P1 | 5 | Week 3 | Done
FE-023 | 5 · Admin File Manager & Upload | Upload modal — drag-drop, multi-file, per-file progress, chunked support | Multi-file drag-drop; >10MB chunked; individual progress bars; green check on complete. | P1 | 4 | Week 3 | Done
FE-024 | 5 · Admin File Manager & Upload | Version history panel — list versions with date/uploader/size, download | Slides in from right; each version shows number, timestamp, uploader, download button. | P2 | 3 | Week 3 | Done
FE-025 | 5 · Admin File Manager & Upload | Audit Log viewer — cursor pagination, filters, CSV export | CSV exports current filter; chips show active filters; row expands JSON diff. | P2 | 3 | Week 3 | Done
FE-026 | 5 · Admin File Manager & Upload | Broadcast Notification page — compose + send to All or a department | Multi-select dept dropdown; live preview card; delivers instantly to connected users. | P2 | 2 | Week 4 | Done
FE-027 | 6 · Admin: CMS Editor & System Config | CMS Editor — 5-tab layout (Hero / Gallery / Banner / Info / Sections) | Save calls PUT /cms/:blockKey; landing page updates via WS without reload. | P2 | 4 | Week 3 | Done
FE-028 | 6 · Admin: CMS Editor & System Config | CMS live preview panel — landing page in iframe alongside editor | Refreshes on every save; desktop/mobile width toggle. | P3 | 3 | Week 4 | Done
FE-029 | 6 · Admin: CMS Editor & System Config | System Config panel — Upload limits, Security, Email, HDD Sync | Each setting reads current DB value; save calls PUT /admin/settings/:key. | P2 | 3 | Week 4 | Done
FE-030 | 6 · Admin: CMS Editor & System Config | Role Manager — 20-key grouped permission grid, assign users | 5 categories of checkboxes; typeahead user picker; saves invalidate permission cache. | P2 | 2 | Week 4 | Done
FE-031 | 7 · User Dashboard | User home — assigned dept cards, recent files, quick search bar | Cards show count + last-updated; recent shows last 5 uploads; search pre-fills query. | P1 | 3 | Week 3 | Done
FE-032 | 7 · User Dashboard | Dept file browser — folder tree, grid/list, breadcrumb, sort/filter | Tree renders FOLDER nodes; no files visible outside assigned depts. | P1 | 5 | Week 3 | Done
FE-033 | 7 · User Dashboard | File Preview modal — PDF.js, image, video, text/CSV | PDF page nav; image zoom; HTML5 video; office files show metadata + download; logs to audit. | P1 | 4 | Week 3 | Todo
FE-034 | 7 · User Dashboard | Search page — full-text results, operator chips, history | Chips render below search bar; last 20 searches suggested on focus; results show badges. | P1 | 3 | Week 4 | Todo
FE-035 | 7 · User Dashboard | /notifications page — 5 tabs, date groups, mark-read | Per-category unread badge; Mark-all/Clear-read; linked notification opens file + marks read. | P2 | 4 | Week 4 | Todo
FE-036 | 7 · User Dashboard | Bell badge (Sidebar) + Topbar dropdown (5 recent + View all) | Numeric badge hides at 0; dropdown updates via WS push, no polling. | P2 | 2 | Week 4 | Todo
FE-037 | 1 · Design System & Project Setup | Toast overlay — bottom-right stack, progress bar, auto-dismiss, pause-on-hover | Max 5 visible, overflow queued; hover pauses timer; 4 status variants. | P2 | 2 | Week 4 | Todo
DB-001 | 8 · Database & Core Infrastructure Setup | PostgreSQL schema design — users, departments, hdd_nodes, files, roles, audit_log, notifications | ERD reviewed and approved; all FKs and indexes defined; schema matches FE data contracts. | P1 | 3 | Week 1 | Done
DB-002 | 8 · Database & Core Infrastructure Setup | Migration framework setup (Prisma/Knex) + seed data for local dev | migrate up/down both succeed; seed creates 1 super-admin, 2 depts, sample files. | P1 | 3 | Week 1 | Done
DB-003 | 8 · Database & Core Infrastructure Setup | Docker Compose — Postgres, Redis, backend API, frontend dev containers | docker compose up boots all services; frontend reaches backend on first try. | P1 | 3 | Week 1 | Done
DB-004 | 8 · Database & Core Infrastructure Setup | Environment & secrets config — .env schema, JWT secret, DB URL, HDD mount paths | .env.example documents every key; app fails fast with a clear error if one is missing. | P1 | 2 | Week 1 | Done
DB-005 | 8 · Database & Core Infrastructure Setup | Redis setup — session/token store + pub-sub channel for CMS & notification WS push | Session lookups hit Redis; a publish on the CMS channel is received by a subscribed client. | P1 | 3 | Week 1 | Done
DB-006 | 8 · Database & Core Infrastructure Setup | CI/CD pipeline — lint + test + build on PR, auto-deploy to staging on merge | PR blocked on failing lint/tests; merge to main deploys to staging within 10 min. | P2 | 4 | Week 2 | Todo
DB-007 | 8 · Database & Core Infrastructure Setup | API mock/contract layer — OpenAPI spec matching every FE-* endpoint | Spec covers all endpoints referenced in Phase 1 FE tasks; mock server validates against it. | P1 | 3 | Week 1 | Done
DB-008 | 8 · Database & Core Infrastructure Setup | Logging & health monitoring — structured logs, /health endpoint, error alerting | Logs are JSON-structured; /health returns DB + Redis status; alert fires on 5xx spike. | P2 | 3 | Week 2 | Todo
| Total Story Points: |  |  |  | 136
| Tasks Done: |  |  |  | 35
| Tasks Todo/In Progress/Blocked: |  |  |  | 10
| SP Completed: |  |  |  | 107

## Scope & Decisions
ID | Issue / Decision | Observed from Sources | Tracker Treatment | Severity | Source
SPEC-001 | V1 task-count inconsistency | V1 cover page says 72 tasks / 168 SP; the 13 section headings sum to 80 tasks / 197 SP; the individual task-row SP values sum to 185 SP. | Use 80 task rows and 185 task-row SP as the operational tracker baseline; keep the 72/168 and 197 figures visible as source discrepancies until the V1 DOCX is corrected. | High | V1 DOCX section tables
SPEC-002 | Database technology mismatch | Existing Phase 1 tracker has PostgreSQL schema/Prisma/Knex language, while V1 explicitly requires MySQL 8.0. | Treat existing DB schema work as rework/porting, not completed V1 backend work. | Critical | Existing tracker + V1 DOCX
SPEC-003 | Role scope mismatch | V1 backend explicitly limits V1 to ADMIN and USER; architecture defines five access levels and later custom roles. | Do not block V1 on Dept Admin/Guest/Read-Only/custom-role implementation unless project owner changes scope. | Critical | V1 DOCX + Architecture Ch. 4/16
SPEC-004 | Redis strategy mismatch | V1 task list explicitly requires Redis token blacklist + pub-sub; architecture Ch. 13.3 says Redis token blacklist is deferred. | For this tracker, follow the V1 complete task list because it is the stated authoritative execution plan. | High | V1 DOCX + Architecture Ch. 13.3
SPEC-005 | Role Manager frontend scope | Existing FE-030 proposes a 20-key role/permission manager derived from architecture custom roles, which is beyond the V1 ADMIN/USER backend scope. | Keep FE-030 as V2/deferred or revise it to the V1 department-access model. | High | Existing tracker + Architecture Ch. 16
SPEC-006 | OpenAPI completion level | Existing DB-007 is marked Done but says it only covers endpoints referenced by Phase 1 FE tasks; V1 acceptance requires all 45 endpoints. | Keep IN-007 as Partially Done until all 45 V1 endpoints and schemas are present. | Medium | Existing tracker + V1 DOCX
SPEC-007 | No deadline supplied | Neither source specifies a project deadline. | Tracker intentionally has no due-date/deadline field; status, source week and owner are used instead. | Info | User instruction + source files